Time Reporting System

Project Epic Plan

4 Developers  ·  6 Days  ·  19 Features  ·  5 Epics

Team Roles

| Developer | Focus |
| --- | --- |
| Dev A | Backend Lead |
| Dev B | Backend |
| Dev C | Frontend Lead |
| Dev D | Frontend |

Epic 1 — Foundation

Days: Day 1   Goal: Project runs, DB is ready, login works

| Feature | Dev | Notes |
| --- | --- | --- |
| F01 Project Setup + Docker | A | Monorepo, docker-compose, 3 services up |
| F02 Database Schema (all 15 tables + seeds) | B | Knex migrations, seed admin user |
| F03 Auth — Backend | A (PM) | JWT, refresh token, bcrypt, RBAC middleware |
| F03 Auth — Frontend | C | Login page, AuthContext, ProtectedRoute, axios interceptor |

✔ Milestone: docker-compose up runs, admin can log in, JWT works.

Epic 2 — Admin Entity CRUD

Days: Day 2   Goal: Admin can manage all master data

| Feature | Dev | Notes |
| --- | --- | --- |
| F04 Users — BE | A | CRUD endpoints, role assignment, reset password |
| F05 Clients + F06 Projects + F07 Tasks — BE | B | 3 simple CRUD modules (same pattern) |
| F04 Users — FE | C | User list, create/edit form, reset password dialog |
| F05 + F06 + F07 + F08 — FE | D | Clients, Projects, Tasks pages + Assignment matrix |
| F08 Assignments — BE | B (shared) | user_task_assignments table, toggle active |

✔ Milestone: Admin can create users, clients, projects, tasks, and assign users to tasks.

Epic 3 — Time Reporting Core

Days: Days 3–4   Goal: Employees can log, view, and report time

| Feature | Dev | Day | Notes |
| --- | --- | --- | --- |
| F09 Daily Time Entries — BE | A | 3 | POST/GET/PATCH/DELETE, overlap detection, quota calc |
| F12 Absence Reporting — BE | B | 3 | Absence CRUD, file upload (attachments table) |
| F09 Daily Report Page — FE | C | 3-4 | ReportForm, ExistingEntriesList, time picker, validation |
| F11 Monthly View — FE | D | 3 | Calendar grid, totals per day, color states |
| F12 Absence UI — FE | D | 4 | AbsenceForm, DocumentUpload, AbsenceList |
| F09 BE edge cases | A | 4 | overlapDetector.js, durationCalculator.js |

✔ Milestone: Employee can log a workday, see monthly view, report an absence.

Epic 4 — Submission & Approval Lifecycle

Days: Day 5   Goal: Weekly submit → admin approves/rejects → month locked

| Feature | Dev | Notes |
| --- | --- | --- |
| F13 Weekly Submission — BE | A | POST /weekly-submissions, status machine (draft → submitted) |
| F14 Approval — BE | B | PATCH approve/reject, rejection_reason stored |
| F10 Timer — Full-stack | B (PM) | active_timers table, start/stop, create entry on stop |
| F13 Weekly Submit UI — FE | C | WeeklySubmitBar, QuotaProgressBar, submit button |
| F14 Admin Approval UI — FE | D | WeeklyReviewCard, RejectReasonDialog, approve/reject actions |

✔ Milestone: Full lifecycle works — employee submits week → admin reviews → approved/rejected.

Epic 5 — Admin Operations & Polish

Days: Day 6   Goal: Lock months, export data, dashboard overview, audit trail

| Feature | Dev | Priority | Notes |
| --- | --- | --- | --- |
| F15 Month Lock/Unlock — BE+FE | A + D | HIGH | month_locks table, lock blocks edits |
| F16 Admin Dashboard — FE | C | HIGH | Submission status table, pending reviews count |
| F17 Audit Log — BE+FE | B + D | MEDIUM | Auto-log middleware planned in F03 middleware layer |
| F18 Export Excel/PDF — BE | A* | MEDIUM | json→xlsx, jsPDF (best-effort) |
| F19 Notifications + Holiday Settings | B* | LOW | Can ship without this |

✔ Milestone: Production-ready core system. F18/F19 are best-effort only if E1–E4 are solid.

Summary

| Epic | Days | Features | Priority |
| --- | --- | --- | --- |
| E1 Foundation | Day 1 | F01, F02, F03 | CRITICAL |
| E2 Admin CRUD | Day 2 | F04, F05, F06, F07, F08 | CRITICAL |
| E3 Time Reporting | Days 3–4 | F09, F11, F12 | CRITICAL |
| E4 Submit & Approve | Day 5 | F13, F14, F10 | CRITICAL |
| E5 Admin Ops | Day 6 | F15, F16, F17, F18*, F19* | HIGH/MEDIUM |

⚠  Key Risk: F09 (Daily Time Reporting) is the heaviest single feature — overlap detection, cross-midnight entries, quota calculation. Protect Day 3 for this; don't let it slip to Day 4 or Epic 4 gets squeezed.